## Sheet1
| CONTRACT : | PRINCE BUTHELEZI MALL
INSTALLATION OF 2.6 MW SOLAR SYSTEM
| Program no: | 1
| Duration | 11 | WEEKS
| Extension of time | 14 | DAYS
| Completion date: | 18/04/2026
ACTION |  | QTY | UNIT | DUR | START | STOP | 2026-02-01 | [29 empty] | 2026-03-01 | [30 empty] | 2026-04-01
|  |  |  | DAYS |  |  | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6 | [6 empty] | WEEK 7 | [6 empty] | WEEK 8 | [6 empty] | WEEK 9 | [6 empty] | WEEK 10 | [6 empty] | WEEK 11 | [6 empty] | WEEK 12 | WEEK 13 | WEEK 14
[7 empty] | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
1 | CONTRACTUAL
1.1 | Contract
1.2 | Signing of contract |  |  | 0
[7 empty] | WEEK 1 7: S; WEEK 1 8: S; WEEK 2 13: F; WEEK 2 14: S; WEEK 2 15: S; WEEK 3 16: M; WEEK 3 21: S; WEEK 3 22: S; WEEK 4 28: S; WEEK 4 1: S; WEEK 5 7: S; WEEK 5 8: S; WEEK 6 14: S; WEEK 6 15: S; WEEK 7 16: M; WEEK 7 17: T; WEEK 7 21: S; WEEK 7 22: S; WEEK 8 27: F; WEEK 8 28: S; WEEK 8 29: S; WEEK 9 30: M; WEEK 9 4: S; WEEK 9 5: S; WEEK 10 10: F; WEEK 10 11: S; WEEK 10 12: S; WEEK 11 13: M; WEEK 11 18: S | S
2 | SITE ESTABLISHMENT
2.1 | Site establish & induction |  |  | 1 | bar: WEEK 1 2
2.2 | Storage and material on site |  |  | 3 | bar: WEEK 1 3 to WEEK 1 4; WEEK 2 12
2.3 | Setting out of works and roof reports |  |  | 4 | bar: WEEK 1 4; WEEK 1 6; WEEK 2 10; WEEK 4 23
3 | CONSTRUCTION
| Rooftop |  | m
3.1 | Install walkways per zone @ 67m/day | 1210 |  | 18 | bar: WEEK 1 5 to WEEK 2 12; WEEK 3 18 to WEEK 4 27
3.1 | Install cable trays @ 59m/day | 833 | m | 14 | bar: WEEK 2 11 to WEEK 2 12; WEEK 3 17 to WEEK 4 28
3.2 | Install panels per zone@154/day | 4320 |  | 28 | bar: WEEK 1 2 to WEEK 2 12; WEEK 3 17 to WEEK 6 13
3.4 | Earthing and bonding |  |  | 5 | bar: WEEK 3 18; WEEK 4 24; WEEK 4 27; WEEK 5 4; WEEK 7 18
3.5 | String wiring back to inverters |  |  | 22 | bar: WEEK 3 20; WEEK 4 23 to WEEK 4 24; WEEK 7 18 to WEEK 8 26; WEEK 9 31 to WEEK 10 9
INVERTERS & AC CABLING
3.6 | Install inverters |  |  | 2 | bar: WEEK 1 6 to WEEK 1 7
3.7 | Install AC cable trays & cabling |  |  | 7 | bar: WEEK 1 8 to WEEK 2 9; WEEK 3 17 to WEEK 3 21
3.8 | Comms & monitoring
3.9 | Install communication cabling |  |  | 2 | bar: WEEK 3 18 to WEEK 3 19
3.10 | Install irriadiance equipmentt |  |  | 1 | bar: WEEK 7 18
3.12 | Set up meteocontrol |  |  | 1 | bar: WEEK 7 18
3.13 | Integration of all equipment onto |  |  | 1 | bar: WEEK 7 19
monitoring platform
4 | TEST AND COMMISSION
4.1 | Test installation as per requirement |  |  | 7 | bar: WEEK 8 25; WEEK 9 2; WEEK 10 8 to WEEK 10 9; WEEK 11 14 to WEEK 11 16
4.2 | Test monitoring and production |  |  | 3 | bar: WEEK 11 14 to WEEK 11 16
5 | HAND OVER
5.1 | PC handover
1
WEEK ENDS
OFF WEEK ENDS-PRETORIA
HIGH PRIORITY PANEL INSTALLATION
COMPLETION DATE